## Sheet1
S No | Feature | Description | State | Duration (Hr)
1 | Products Component | Show list of products on homepage | open | 2
2 | Filter Component | Filter products based on their sizes and sort by price | open | 2
3 | Cart Component | Show selected items in the cart on the right sidebar | open | 3
4 | Add Animation | Animated products list and adding to cart | open | 2
5 | Add Model | Show modal when user clicks on a product | open | 2
6 | Checkout Form | Show checkout form to get buyers data | open | 2
7 | Products Backend | Create a simple backend to send products to frontend | open | 3
8 | Add Redux | Create store, initialState and reducer and redux devtools | open | 2
9 | Add Redux to Products | Move products state to redux | open | 3
10 | Add Redux to Filter | Move filter state to redux | open | 3
11 | Add Redux to cart | Move cart state to redux | open | 3
12 | Create Order | Handle frontend and backend of creating an order | open | 3
13 | Add Admin Section | Use react-router to create two routes for Home and Admin | open | 2
14 | Publish on Heroku | Create MongoDB atlas database and publish Heroku app | open | 3
35